Removal of Five Houses and One Shed located on North Beach Island, Chatham, MA

Cape Cod National Seashore

October 12, 2011 Work session Discussion with Chatham Conservation Commission

Conservation Commission discussion items and clarifications on protocol with Seashore staff:

- Confirmed no stockpiling, staging or equipment storage is to be on town land.

- Commission requested that roads and demolition areas be restored to pre-project conditions, especially town land (commissioners discussed that use of roads on North Beach Island to cross other landowner’s lands has been customary).

- Control of some town landings is through Board of Selectmen.

- Remove leftover debris, lumber, and excess materials loose on properties now.

- Crowell shed was reported to be vacant (since removed by storm conditions).

- Commission desires 7-day advance notice of project start date.

Note:   Some work items will need to be updated because the timeframe of work has been delayed, demolition protocol may be phased, and the shed is now destroyed.

Background information and protocol provided prior to the meeting to the Commission:

Overview

Cape Cod National Seashore management is proposing to remove 5 dune cottages and 1 shed owned by the National Park Service on North Beach Island in Chatham, MA in hazard-prone areas, including the velocity zone.  The project is planned to remove man-made alterations on the natural landform to restore natural coastal processes and eliminate impedance to the landward migration of the barrier beach.  The structures are at risk of substantial property damage during coastal storms, including powerful “northeasters” and hurricanes, so elimination of hazards to the structures, and to public safety and navigation will result from the project.

North Beach Island is a rapidly eroding sand barrier beach island recently separated from the mainland at Nauset Beach since the breach in 2007. The beach, dune and coastal bank landforms are migrating.  Site conditions change with each tidal cycle. Some offshore areas are very shallow, while others drop off to depth quickly. The island is eroding at an approximate average of 80 feet per year in some areas and is fully exposed to the forces of any storms. Because of the rapid rate of erosion, the NPS plans to remove these five houses and one shed before they are destroyed by wave action or other adverse effects of coastal erosion and storms.  This hazard mitigation measure will restore functioning of part of the coastal ecosystem in the North Beach Island area while the underlying land remains; beaches and dunes will be available for reestablishment of vegetation and avian wildlife nesting, foraging, resting, and staging.

There is no alternative to this action that is environmentally responsible – the structures will not last in such a vulnerable, rapidly eroding environment.  If the structures are not lost to storms and are not removed prior to being surrounded by water, then access and permitting restrictions would make the removal more difficult and the project more damaging to the environment.

A fundamental aspect of the federal-state regulatory relationship is that Federal Agencies are exempt from all state and local permitting requirements, except when Congress clearly indicates that the sovereign immunity of the Federal Government is waived.  One instance of such a waiver relates to activities resulting in the discharge or run-off of pollutants as presented in Section 313 of the Clean Water Act codified as 33 United States Code Section 1323 (a).  Thus, when federal actions “result in the discharge or run-off of pollutants” and there are state and local permitting processes (e.g., Conservation Commission) regulating these, the park is subject to those permitting requirements concerning the control and abatement of water pollution.  In terms of activities occurring in wetland areas, the state Wetland Protection Act (WPA), Chapter 131, Massachusetts General Law, Section 40 is far broader in scope than discharge control.  The interests protected through this law include storm damage control, wildlife protection, and other interests beyond pollutants discharge.  The sovereign immunity of the Federal Government has not been waived for any of the above mentioned interests.  As a result, the park is exempt from the requirement of consulting the Conservation Commission (i.e., filing a Notice of Intent) for projects affecting the coastal bank or related issues, except when the discharge of pollutants is a concern, even though the activity would otherwise be subject to the review authority of the Conservation Commission if the same activity were being conducted by a non-federal entity on non-federal land.

Therefore, a courtesy consultation with the Conservation Commission is appropriate, rather than a WPA Notice of Intent permitting process since the project will not involve water quality pollutant discharge or run-off.  It should also be known that transient federal and state protected species will not be affected due to the time of year of the activity.  And, the NPS is completing its National Environmental Policy Act categorical exclusion and National Historic Preservation Act Section 106 compliance analysis and documentation.

Project Description

The project scope of work is to remove and dispose of the five houses owned by the National Park Service (NPS) known as the Bloomer, Carroll, Crowell, Dubis and Lumpkin cottages, complete and in their entirety, from the north end of North Beach Island in Chatham, MA.  A small NPS-owned shed on the eastern shore of the island that is currently used by the Town may also be included in the removal contract.   The cottages have been under one-year Special Use Permits for private occupancy that have been issued for about 6-13 years, and the shed has been used by the Chatham Police Department under agreement for almost 5 years for support of shorebird monitoring activities. NPS has notified the occupants that permits and agreements will not be renewed; all tenants will have removed personal possessions and vacated the structures prior to commencement of demolition.

All five cottages and the shed were rebuilt on pilings in the early 1990s, after being destroyed during the No Name Storm of 1991. Due to the recent construction, asbestos and lead paint are not expected to be present.  The structures were rebuilt on 12” diameter by 24’ long cross-braced pilings.

A contract will be issued, and equipment and personnel will be brought to the island by boat and barge.  A crane may be used.  Tracked excavators will be utilized to carry debris to dumpsters.  A demolition plan/protocol is required to be approved by the NPS prior to contractor action, including: disposal destination for all material removed from island, location of access point(s) on island, routes to be used in demolition and removal, stockpile area(s) for material removed prior to demolition, areas of disturbance during demolition and removal.  Equipment and heavy machinery may be removed from the island each working day to the extent practical, or stored above high water at approved staging areas.

The preliminary protocol includes that NPS and the Contractor shall establish that every effort shall be made to minimize both short-term and long-term impacts to vegetation, surface topography and any wetland buffer areas on the island during the performance of the contract.  The project will not alter salt marsh, no work will be allowed within established wetlands, and there will be no excavation of intertidal areas. The contractor is required to access the structures using the beach near the high water mark and/or use existing established paths and sand roads.  Revegetation with beach grass will be included in work areas disturbed by the project.

The NPS preferred timetable for this activity is between November 2011 - January 15, 2012.

Requirements to be included in the Scope of Work

Contractor shall familiarize themselves with site conditions.  Prior to commencement of any work, the Contractor will submit a detailed work protocol for approval by NPS listing the following in detail:

- type, size and quantity of equipment to be used on island, including make, model and any accessories,

- type, size and quantity of equipment to be used to transport equipment to and from the island, including make, model and any accessories, and length of time equipment will be on island shore,

- type, size and quantity of equipment to be used to transport demolition debris, including make, model and any accessories,

- disposal destination for all material removed from island,

- a copy of marked up map or aerial photo showing:

- location of access point(s) on island,

- routes to be used in demolition and removal,

- stockpile area(s) for material removed prior to demolition,

- areas of disturbance during demolition and removal

note: (see the attached map provided to the Commission for recommendations)

- landside water access point (Ryder’s Cove Landing and Fish Pier are two Chatham locations),

- schedule of all activities, including dates and durations.

Impacts to the island shall be minimized to the greatest extent possible.  Contractor will utilize beach area and existing established paths.   Work will not occur within established wetlands.  Private land must be avoided.  Town land will be crossed but not used for staging or stockpiling.  Any proposed additional access routes shown on attached site map shall be flagged at least one week in advance by contractor for review, approval and possible adjustment by NPS.  Equipment shall be inspected prior to mobilization, and equipment that is found to be leaking fuel, oil, lubricant, or other contaminant shall not be utilized in the project area.

Contractor is to set up demolition equipment in areas on the island owned by the federal government already disturbed by permittees’ use of the properties to the greatest extent possible.  Stockpile sites shall be located in areas already disturbed.  Areas to be used or proposed to be newly disturbed by demolition and removal activities shall be flagged at least one week in advance by contractor for review, approval and possible adjustment by NPS.

Prior to demolition, Contractor will remove and  stockpile the following from the above-listed buildings:

- windows and any other glass,

- white goods; including but not limited to stoves, refrigerators, washers, dryers, dishwashers, space heaters and any other appliances, incinerating toilets, etc.

- oil, propane and any other fuel tanks,

- any other metal or other non-burnable items contained within or on the structures, such as antennas, storage containers, etc.

Contractor will also remove pilings in their entirety and dispose of them off-site.  All demolition materials shall become the property of the contractor, and shall be disposed off-site at an appropriate facility.  Disposal of any of the above mentioned items must be done in accordance with all Massachusetts Department of Environmental Protection (MA DEP) and Environmental Protection Agency (EPA) rules and regulations.

Attachments

USGS Quad map and September 2011 photos

2 CCNS GIS maps (one with shoreline and elevations, and one marked-up with recommended access routing and protocol details)

FEMA FIRM & Mass DEP wetlands maps

Burning Option

The NPS may pursue plans to burn one or more of the structures, jointly with the Chatham Fire Department and under Mass Department of Environmental Protection (DEP) permit, to reduce the amount of material that must be removed and disposed of.  If burning is not used as an option, structures will be removed by mechanical means by a contractor.

The NPS burning operation may be used after non-combustible material is removed from the structure(s), as a training exercise to reduce the quantity of demolition debris to the greatest extent possible.  The Contractor shall perform the following activities after completion of burning:

- remove all remains after burning, including cinders, ash, uncombusted wood debris, etc,

- remove all previously stockpiled material (this activities can occur prior to burning or in conjunction with removal of post-burning debris),

- utilize a magnet of suitable magnetic strength to ensure all ferrous metals from burned structures have been collected and removed,

- collect and remove all other un-combusted materials, metal or otherwise,

- remove and legally dispose of all material resulting from the demolition of five houses from island,

- provide written supporting documentation of disposition of removed materials,

- remove all equipment and materials associated with the work of this contract,

- rake all disturbed areas smooth,

- leave site in condition and appearance similar to surrounding area.

North Beach Island Tracts in Chatham

Properties Owned by USA Currently Under an Annual Special Use Permit

Property Improvements and Dimensions

| NPS Tract Number | Structure name | Property Location | Town | Acres | Building Square Footage | Deck Square Footage |
| --- | --- | --- | --- | --- | --- | --- |
| 41-8672 | Crowell cottage, or camp | North Beach | Chatham | 3.0 | 784 (560 as per 2004 NPS Appraisal) | 976 |
| 41-8671 | Lumpkin cottage | North Beach | Chatham | 1.8 | 576 | 867 |
| 41-8103 | Bloomer Cottage | North Beach | Chatham | 0.7 | 576 | 852 |
| 41-8106 | Carroll cottage | North Beach | Chatham | 0.69 | 576 | 716 |
| 41-8107 | Dubis cottage | North Beach | Chatham | 1.72 | 576 | 1,188 |

Notes:

- Source of square footage information is the Town of Chatham Assessor’s Database.

- 8 other properties with Reservations of Use and Occupancy have transferred to the NPS as some were

buried in sand, land eroded (such as Scott and Achilles in summer 2007), or were lost in No Name Storm of 1991 and were not rebuilt, etc.

- In addition, Tract 41-8673, informally known as the Crowell shed, is also owned by NPS and is used under a Cooperative Agreement by the Chatham Police Department for shorebird protection monitoring gear.